## Slide 1: Automated infill optimization for a marine 3D seismic survey
Dave Ridyard and Damian Hite

## Slide 2: Presentation Outline
2D / 3D Project description and challenges
Estimating infill
Reducing infill
Final thoughts

## Slide 3: Project Description Overview
Unobstructed frontier area
Offshore Labrador, Canada
1,700 sq.km. 3D
Regional 2D program

## Slide 4: Project Description Challenges
Short acquisition season : 60-90 days
Currents around shelf slope
  Infill uncertainty

## Slide 5: 2D Design
5,591.3 km
10km streamer
Est. 35.6 Days (+Mobilization)
Environmental impact
Shots 223,652
Area of insonification 104,118.2 sq.km.
Area of operations 117,985.8 sq.km.

## Slide 6: 3D Design
Baseline design
  5 sources
  10 streamers
  2 racetracks (AB-BA)
  3,780 Line km (including run outs)
  Downtime model
    15% weather standby
    5% technical downtime
  Approx 30.3 days vessel time
  Environmental impact
    302,365 shots
    Area of insonification 2,296 sq.km.
    Area of operations 2,925 sq.km.

## Slide 7: Infill estimation
Temporal and spatial current variation
Ocean currents
Tidal currents

## Slide 8: Current model applied to Survey Design Based on actual survey timing
Inline and crossline current vectors computed for every shot.
(Only crossline component shown.)

## Slide 9: Current model applied to Survey Design Based on actual survey timing
Mismatched feathering on adjacent lines results in missing coverage
Infill lines required

## Slide 10: Current model applied to Survey Design Based on actual survey timing
Mismatched feathering on adjacent lines results in missing coverage
Infill lines required

## Slide 11: Current model applied to Survey Design Based on actual survey timing
Mismatched feathering on adjacent lines results in missing coverage
Infill lines required

## Slide 12: Current model applied to Survey Design Based on actual survey timing
Mismatched feathering on adjacent lines results in missing coverage
Infill lines required

## Slide 13: 3D Binning
Coverage specifications designed based on Fresnel zone/5D interpolation considerations.

## Slide 14: 3D Binning
Coverage specifications designed based on Fresnel zone/5D interpolation considerations.
Offset
0 m
8000 m

## Slide 15: Infill estimated
52 Infill line segments required
Short, inefficient line segments
27% of primary line kms
1,009 kms
62% of primary acquisition time
18.9 days
Total Project Time : 71.1 days
2D + 3D + Infill
Excludes reconfiguration/mobilization

## Slide 16: Presentation Outline
2D / 3D Project description and challenges
Estimating infill
Reducing infill
Final thoughts
Current Analysis
TSP
Generate Source & Receiver
Apply Downtime Model
Time and Motion
Create Survey (Towed Streamer)
Apply Currents
Infill Analysis
Export Infill Shape
Import Infill Plan
TSP (Infill)
Binning

## Slide 17: Impact of Number of streamers
Parallel streamers
6
10
14
5 sources
Conventional narrow towed
No streamer steering
6
10
14

## Slide 18: Impact of Number of streamers
Parallel streamers
6
10
14
5 sources
Conventional narrow towed
No streamer steering
Assumptions
10% weather downtime
5% technical downtime
Streamers | Acquisition (Days) | Estimated Infill (Days/%) | TOTAL (Days)
6 | 50.7 | 23.9 / 47% | 74.6
10 | 30.3 | 18.9 / 62% | 49.2
14 | 21.7 | 12.9 / 59% | 34.6
6
10
14

## Slide 19: Impact of Streamer Steering Strategy
10 Streamer 5 sources | Estimated Infill (Days/%) | TOTAL (Days)
Streamer steering (2o) | 13.7 / 45% | 44.0
Natural feather | 18.9 / 62% | 49.2
Streamer fanning (2o) | 1.1 / 4% | 31.4
Parallel Fanned
Steered
Natural feather
Fanned

## Slide 20: Impact of Streamer Steering Strategy
Infill plan
Natural feather
Infill plan
Fanned streamers (2o)

## Slide 21: Marine Streamer Infill Optimization Summary
Integrated 2D and 3D program planning is critical to success in time limited projects
In-fill is a fact of life
… but it does not need to be a surprise !
  Plan for it
  Budget for it
  Minimize it !
Other options to consider
  Impact of in-line currents
  Overlapping swaths(N+2 streamers, Roll N)
  Vessel steering strategies
  Feather matching strategies
  Compressive sensing
  Offset dependent bin size
  Fresnel zone binning
  Wide tow source